ENVIRONMENTAL IMPLICATION STUDY (EIS): STREAMLINING THE PROCEDURAL GUIDELINES

- The Proponent submits a notification of intent to the Ministry of Environment to conduct Environmental Implication Study – the application should provide technical briefs on the project and the scope of the EIS as the ToR for the project;

- Payment of non-refundable fee of Four Hundred and Fifty Thousand Naira (₦450,000) in bank draft for registration and certification, which must come alongside the application;

- Site verification by the Ministry;

- Review of the project technical briefs and the scope of work by the Ministry to approve the Terms of Reference for the EIS and conveyance of same to the proponent;

NB: (c) and (d) should be done within two (2) weeks after (a) and (b)

- Field study (One season): Data gathering and environmental sampling must include health, social and economic data as well as collection of relevant and appropriate environmental samples (in quantity and scope), submission of samples to registered and accredited Laboratory for analyses. The second season should be referenced from an approved report of a still valid project in proximity to the project for which certification is sought – timeframe dependent on Proponent but must not be more than one month after the ToR was communicated to the Proponent.

NB: At least one authorized Personnel from the Ministry must witness the exercise to authenticate it;

- Submission of draft EIS Report: The report should be accompanied with a bank draft of Three Hundred and Fifty Thousand Naira (N350,000.00).  The draft EIS report should be submitted within two (2) months of the field study;

- Review of the draft report by the Ministry:

NB: Review to be done within one month of submission of the draft EIS Report.

- Submission of Review Exercise Report for approval or otherwise and conveyance of same to proponent – within two weeks of Review Exercise;

- Forwarding of the harmonized Review Meeting comments to the Proponent within two (2) weeks after conclusion of h;

- Submission of Final EIS report to the Ministry within two (2) weeks of i;

- Executive Report of the project forwarded for approval upon satisfactory rating of the final report within (2) weeks of j;

- First Impact Mitigation Monitoring (IMM): This should be conducted three months of construction phase of the project and feedback forwarded to the Proponent within two (2) weeks after the exercise;

- Second Impact Mitigation Monitoring (IMM): This should be conducted three months into the operation phase of the project;

- Certification of project: This should be done upon closure of IMM.

NB: Issuance of Environmental Certificate to be done within two weeks of closure of IMM.

- Renewal of Certificate with submission of Bank Draft of N250,000.00 every five years.

- Communication with the Proponent

The Ministry shall feedback the Proponent at every phase of the EIS process completed stating the next phase.

- Penalty for the default on the part of Proponent

              - Clearing of the site before EIS Approval – Maximum of ₦1,000,000.00 subject to the approval of the Honourable Commissioner for Environment;

              - Failure to conduct Field study/Data Gathering within one month of receipt of ToR from the Ministry - ₦100,000.00;

              - Failure to submit the draft EIS report within two months after the field study/Data gathering - ₦100,000.00